## Cover page
WORKING DOCUMENT
Expert Group Swimway (EG-Swimway 21-1)
2021-10-14
Agenda Item: | 6. Roadmap
Subject: | EG-Swimway work plan 2021/22
Document No.: | EG-Swimway 21-1/6
Date: | 2021-11-03
Submitted by: | CWSS
This document contains a draft work plan for EG-Swimway 2021/22 which is based on the CWSS work plan submitted to WSB 32 (WSB 32/7 Annual workplan by CWSS). In addition, this work plan contains a timeline for planning of meetings within the German presidency, until 2022.
Proposal: | EG-Swimway is invited to agree on topics and products to be delivered until the Trialteral Governmntal Conference 2022.

## EG-S work plan
EG-Swimway Workplan 21-22 (v. November 2021)
Table: Work plan 2021/22 of the Expert Group Swimway (EG-Swimway) with activities/deliverables/products. This version contains amendments by CWSS in 2021. A column with reference to the Terms of Reference EG-Swimway is inlcuded (col G). It further contains a timeline and scheduled meetings of the Wadden Sea Board (WSB) for planning of EG-Swimway activities and meetings for the entire German presidency (columns J ff). On-going activities over one year (2021) continue in a separate line (2022).
28.11.-1.12. TGC
§ LD (full text visible as comment) | Activities / Deliverables from approved TWSC WORKPLAN 2019-22 and additional products/events/projects | 2021 | 2022 | Planned activities/deliverables | Task/Deliverable # | Responsible at CWSS | Status | Nov 21 WSB 34 18.11. EG-Swim 21-1 | Dec 21 | Jan 22 | Feb 22 | Mar 22 WSB 35 10.3. | Apr 22 WSB TBD | May 22 | Jun 22 | Jul 22 | Aug 22 WSB 36 26.8. | Sep 22 WSB 37 TBD | Oct 22 WSB 38 6.10. | Nov 22 WSB 39 29/30.11. | Dec 22
13 | ToR and work programme for EG Fish | 2021 |  | Assignment external coordinator / Terms of Reference | ToR WG-Swim. | JB | completed
13 | QSR thematic report fish | 2021 |  | QSR thematic report fish | T4/D3 | JB | completed
13 | Recommendation for operational fish monitoring programme(s) under TMAP | 2021 |  | Assignment external coordinator / Workshops/TMAP fish monitoring proposal | T2/D2 | JB | in progress |  | Delivery of proposal to TG-MA
13 | Activity plan for implementation of Swimway Vision and Action Programme | 2021 |  | Assignment external coordinator / funding stratgey / common project proposal / | T7/D5 | JB | postponed
13 | Activity plan for implementation of Swimway Vision and Action Programme |  | 2022 | Assignment external coordinator / funding stragtegy / common project proposal/ Mid term review Swimway programme | T7/D5 | JB | scheduled |  |  | Include in Mid term review?
13 | Progress towards reaching the trilateral fish targets | 2021 |  | Assignment external coordinator / funding stragtey / common project proposal / workshops | T8 | JB | scheduled |  | Update Swimway funding proposal & next steps
13 | Progress towards reaching the trilateral fish targets |  | 2022 | Assignment external coordinator / funding stragtey / common project proposal / workshops / Mid term review Swiimway programe | T8 | JB | scheduled |  |  | Start trilat project historical | Decide on additional project? Grad school |  |  |  |  | End Trilat project historical
13 | Website/Microsite SWIMWAY | 2021 |  | Assignment external coordinator / effective communication | T6/D4 | JB | in progress |  | Draft "main" page
13 | Website/Microsite SWIMWAY |  | 2022 | Assignment external coordinator / effective communication | T6/D4 | JB | scheduled |  |  |  |  | Draft sub-pages | [5 empty] | Final microsite
13 | Communication platform |  | 2022 | Funding stragtey / common project proposal / workshops / effective communication | T5/D4 | JB | scheduled
13 | Implementation of Swimway Vision and Action Programme |  | 2022 | Assignment external coordinator / Funding strategy/ Mid term review Swimway | D1, D5 | JB | scheduled |  |  | Draft mid-term review |  | Final mid-term review | [7 empty] | TGC -side event mid term review?
42 | Policy Assessment Report (PAR) | 2021 |  | Installment of Drafting Group and preparing 1st draft of the MD Wilhelmshaven 2022 |  | BB | in progress | [12 empty] | PAR final
43 | Draft MCD for national consultation |  | 2022 | Final draft of MD |  | BB | scheduled | Email consultation: Brainstorm MCD | [11 empty] | MCDfinal | MCDfinal
43 | Trilateral Governmental Conference (TGC) |  | 2022 | Full Conference and Council meeting organised |  | BB | in progress | Email-consultation: Brainstorm side event | [11 empty] | TGC | TGC
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29. Review and monitor the impacts of renewable energy production and energy transportation on the Wadden Sea ecosystem and consider measures to avoid or mitigate possible negative impacts by looking for best environmental practices also with the aim of developing, for example, related common principles to evaluate the impact of high-voltage power cables in the Wadden Sea Area in close consultation with the responsible bodies and stakeholders
Note on A7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23. Make use of all relevant existing monitoring and action programmes, as well as existing action plans, to gain and exchange adequate additional knowledge on sources and impacts of marine litter on the Wadden Sea ecosystem and stimulate and support appropriate measures
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29. Review and monitor the impacts of renewable energy production and energy transportation on the Wadden Sea ecosystem and consider measures to avoid or mitigate possible negative impacts by looking for best environmental practices also with the aim of developing, for example, related common principles to evaluate the impact of high-voltage power cables in the Wadden Sea Area in close consultation with the responsible bodies and stakeholders
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23. Make use of all relevant existing monitoring and action programmes, as well as existing action plans, to gain and exchange adequate additional knowledge on sources and impacts of marine litter on the Wadden Sea ecosystem and stimulate and support appropriate measures
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23. Make use of all relevant existing monitoring and action programmes, as well as existing action plans, to gain and exchange adequate additional knowledge on sources and impacts of marine litter on the Wadden Sea ecosystem and stimulate and support appropriate measures
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22. Substantially reduce the amount of marine litter in the Wadden Sea by the year 2030
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22. Substantially reduce the amount of marine litter in the Wadden Sea by the year 2030
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29. Review and monitor the impacts of renewable energy production and energy transportation on the Wadden Sea ecosystem and consider measures to avoid or mitigate possible negative impacts by looking for best environmental practices also with the aim of developing, for example, related common principles to evaluate the impact of high-voltage power cables in the Wadden Sea Area in close consultation with the responsible bodies and stakeholders
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29. Review and monitor the impacts of renewable energy production and energy transportation on the Wadden Sea ecosystem and consider measures to avoid or mitigate possible negative impacts by looking for best environmental practices also with the aim of developing, for example, related common principles to evaluate the impact of high-voltage power cables in the Wadden Sea Area in close consultation with the responsible bodies and stakeholders