## Projects 2020
TG-WH 32: Status of WH related activities in the Supplementary Budget 2020 (version 12 January 2021)
| Sub- Theme |  | Planned activities/deliverables | UPDATE Status Jan 2021 | Estimated costs 2020 for funding by the states parties |  |  |  | Remarks
Main Theme |  | CWSS Account/PIC (person in charge) |  |  |  | Pledged share D | Pledged share DK | Pledged share NL
WORLD HERITAGE
International Cooperation | UNESCO World Heritage Centre | K135 HM |  | Collaboration continued by supporting WHC activities (renewable energy project, e-meeting on blue carbon). Joint preparation of a site managers meeting on "Climate vulnerability" on 3 December 2020. | 5000 | 2500 | 0 | 2500 | Follow up of marine litter workshop 2018 (communication and awareness rising of marine litter in WH sites) and of the 4th Marine site managers' conference (Sept 2019). The development of a 3-year project is envisaged to define work themes, activities, outputs and results.
| MOU Korea | TMAP K01 HM | Hosting Study visit North- and South Korean experts (probably May 2020). General MOU activities: participation of Wadden Sea experts. Deliverable: Cooperation strategy and activities in the framework of MoU and Yellow Sea | Preparation of study visit started in 2019 but have been on hold since February 2020 (due to Covid-19 crisis). | 12000 | 6000 | 0 | 6000 | A decision on the Korean WH application is expected in July 2021 which may also have effects on the current MoU.Therefore further discussion of concrete activities have been postponed for the time being (joint workshop, costs depending on meeting venue and number of participants), ( indicative 7.000). A preparation of study visit of North/-South-Korean experts (about 20) has not yet been finalized, funding and organization of the entire 10-day trip will be done by Korea. CWSS plans to host a 2-day workshop with Korean and Wadden Sea managers and scientists (costs about 5.000 €)
| MOU Mauretania | K127 GL | Development Communication plan 2020-2022 with support of UNESCO. | Ongoing. Coordinated by the Flyway steering group. | 5000 | 1666 | 1666 | 1666 | Communication plan 2018-2020 delayed. Produce a documentary on the importance of the three sites for the conservation of migratory birds in four languages (Arabic, French, English, Portuguese). - Produce joint communication media for general public and agencies. - Integrating the three sites PNBA, Wadden Sea and Bijagós with the international networks of centres of environmental interpretation. - Integrate the three sites Wadden Sea, PNBA and Bijagós into the international networks of flyway initiatives. - Development of raising awareness for PNBA in Nouakchott.
| Wadden Sea Flyway Initiative | K107 GL | Capacity building of WH sites along EAF/training courses/application proposal for IKI project"WSFI capacity building project 2020-2021. Programme not developed yet. Report on WSFI flyway monitoring at selected critical sites in January 2020 and preparation of 2021 Flyway counting." | Ongoing. Coordinated by the Flyway steering group Report on flyway monitoring published in December 2020 (https://www.waddensea-worldheritage.org/news/first-results-2020-flyway-count-published) | 145000 | 60000 | 10000 | 75000 | "The capacity building will be funded by BMU with € 60,000 in 2020 and € 60,000 in 2021. It will contain several sub-projects: - training and courses bird protection, - management of wetlands, - awareness raising and information centres, - support in conferences (PAOC), - preparation WSFI IKI project, The flyway monitoring 2020 (estimated costs 75.000€ ) is fully supported by LNV (PRW) by a direct assignment to the executive organisation Sovon. The Danish contribution (in-kind amounting to 10.000€) also supports this monitoring programme. Further communication of WSFI by microwebsite is envisaged to be covered by core budget.
|  |  | Establish an overall program, including the financial resources needed, to secure the basic flyway monitoring for the longterm, including flyway-partners. | Ongoing. Coordinated by the Flyway steering group. | 50000 | 16666 | 16666 | 16666 | The financing of the flyway monitoring from 2021 onwards, is not safeguarded and will need alternative resources. Fund raising concept and implementation program needed to ensure continuous flyway monitoring and the value of the past monitoring results.
|  | GL | Arctic WSFI workshop | Postponed due to Covid-19. Coordinated by the Flyway steering group. | 30000 | 30000 | 0 | 0 | Implementation of Flyway Vision in the framework of WSFI. Integration arctic breeding grounds into WSFI. Workshop of WSFI partners with researchers from Arctic countries. Prioritization future support in monitoring, capacity building, research, communication and cooperation. Postponed from 2019 to 2020. Budget already affirmed by Germany in 2019.
WH Brand Management | Brand Activation and Management | K115 WP3 AD | Brand activation various target audiences and stakeholders: - Brand activation guidebook (transnational concept and local implementation) 39,500) - Brand visualization and communication material and modules (e.g. flyers, videos social media) for various target audiences (40,500) - Online branding toolbox for co-branding (47,000) | Branding guidebook (four languages) completed and material is currently being collected being finalized for publishing | 0 |  |  |  | No additional funding from state parties required as it is covered by PROWAD LINK according project work plan 2018 - 2021.
Outreach and Communication | WH Education Strategy | K72 AB | Contract with IWSS (WWF): Implementation of the WH Education Strategy, adopted at the Leeuwarden Conference | Network Group Education and IWSS network meeting postponed to November 2020 (virtual meeting). Development of education material ongoing. New contract with WWF (2020 - 2022) has been concluded in January 2021 (delayed because of VAT issues) | 40000 | 15000 | 10000 | 15000 | Continuation of networking and communication activities, connecting regional education networks. Development and/or update of trilateral interpretation material, according WH Interpretation Strategy 2018. Work plan 2020-2022 to be envisaged at WSB 30. Proposal 2 is agreed upon; increase to €40,000.00/year. (In Germany the share is divided between SH: € 5000, NLPV NDS €5000 and NP HH €5000).
| General Communication and Awareness WH | K1 and K115 WP 2 AB | Transnational communication and awareness activities on World Heritage for various target audiences and involvement of stakeholders in D, DK and NL. Annual stakeholder forum meeting. | Proceeding according PROWAD Link work plan. Annual stakeholder forum 2020 was postponed to 2nd half 2021. Core budget financed activies are website maintenance, redesign of the WSWH leaflet and new WSWH video production. | 0 |  |  |  | No additional funding from states parties required as it is covered by PROWAD LINK (according project work plan 2018 -2021) and by the core budget.
| WH Social Media. | K135 AB | Extension of WH communication on social media channels (Facebook, Twitter, Instagram, Youtube), DNA mapping, sharing and placing contents. Further development of strategy and cooperation with partners (action plan, workshop) | Annual workshop in Hamburg in September 2020. Group in exchange on Covid-19-related strategies for social media. | 7500 | 3750 | 0 | 3750 | Stauts 2019: The 2nd social media workshop was held in January 2019 . As the anniversary campaign coming up, the workshop was used to create an accompanying social media plan. It was decided to hold the next workshop in January 2020. Although limited to a maximum of 8-10 people, the workshop is open to all social media experts of the TWSC. Planned 2020: Annual workshop in January 2020 with support from an external expert - external expertise: 7000€; event catering: 500€.
Develop and enhance sustainable tourism (STS) and new Action Plan | WH awareness raising at yearly ITB (Berlin) | K136 AD | Awareness raising platform Word Heritage stand at ITB (showcasing the trilateral cooperation, non- commercial with partners from regional, national or international level as UNESCO). | ITB March 2020 was cancelled on short notice due to the Covid-19 crisis. Advance payments to ITB have been refunded. Only stand construction has been partly invoiced (production costs €6.000) and was shared accordingly. | 14000 | 7000 | 0 | 7000 | Total costs based on 2019 budget: € 20,000. Basic costs (floor rental) of € 14,000 to be covered by the Trilateral Cooperation (as in 2019). Increasing buying in of partners. (D share: SH 3,000 €, NLPV NDS 3,000 €, NP HH 1,000 €) Connection with stakeholder platform stand provided by PROWAD LINK WP2 (B2B and B2C) (see separate table).
Support Regional Sustainable Development in connection with Nature Protection | Partnership development/Partnership Hub | K01 HM | Establishment of partnership hub. Engaging further strategic partner and development of joint projects. | Coordinated by OPTeam partnership hub. Extended until June 2021 | 20000 | 6666 | 6666 | 6666 | For the establishment of the Partnership Hub and the follow-up of the MOU's signing at 30 June 2019, a coordinating and stimulating effort is required (preinvestment) of an estimated 20.000. Connection with WP 4 of PROWAD LINK.
| PROWAD LINK Project | K115 HM | Co-funding of CWSS activities in PROWAD LINK covering all six work packages (project management, communication, brand activiation, sustainable entrepreneurs, new products and services) (see separate table) | Proceeding according to PROWAD Link work plan. Regular progress reports (#3 submitted on 24 April 2020, #4 on 10 December 2020, becauese further requests, the report had to be resubmitted by 29 January 2021). | 11200 | 5200 | 3000 | 3000 | PROWAD LINK activities of CWSS according project work plan 2018 - 2021 (see separate table). The total CWSS project budget is 865,982 € of which 50% is funded by Interreg (ERDF) . The 50% CWSS self finance is covered by the core budget (staff, travel cost), rest from the first PROWAD project, and from CWSS surplus 2017. This leaves a gap of € 25,500 for the remiaining two years.Proposal to cover the gap in 2020:: Estimated D share from Schleswig-Holstein 5,200 (The Hamburg share of 5000 was already pledged by LoI Prowad Link). Estimated share of 3,000 each from DK and NL.
Remark 1: Items in green are externally financed (see column Remarks for explanations; externally financed might also include the Länder).

## Projects 2021
TG-WH 32: Status of WH related activities in the Supplementary Budget 2021 (version 12 January 2021)
Main Theme | Sub- Theme | Planned activities/deliverables |  |  |  |  | Remarks
|  |  | Total amount granted by state parties. | Pledged Share DE (BMU/Länder) | Pledged share DK | Pledged share NL
WORLD HERITAGE
International Cooperation | UNESCO World Heritage Centre | Collaboration with WH Centre with focus on Marine Programme and Sustainable Tourism programme. Joint online meetings with programme networks | 3000 | 1500 | 0 | 1500 | Due to the pandemic, it will probably not possible to organize joint meetings or workshops with international participation. Instead, focus will be on exchange of experiences via webinars of online network meetings. A closer cooperation with the bi-monthly Marine Sites Managers online meeting is envisaged to present the TWSC work and to enhance the international profile of the Wadden Sea.
| MOU Korea | General MOU activities foreseen to be at very low level due to Covid-19 and taking up by CB. | 0 |  | 0 | 0 | Due to the pandemic, it will probably not possible to organize joint meetings or workshop with international participation. Possible participation of Korean delegation at ISWSS in autumn 2021 (travel, accommodation) will be covered by Korea, conference fee by ISWSS budget). The decision on the Korean WH nomination will probably be taken in mid of 2021 (as the Committee meeting 2020 was postoned to 2021). In case of additional acitivities in 2021, this will be covered by the core budget (budget line WSP/MD/TMAP).
| MOU Mauretania | General MOU activities foreseen to be at very low level due to Covid-19. Update needed of Action Plan with Mauretania. Any costs by CB. | 0 |  | 0 | 0 | Possible participation of Mauretanian delegation at ISWSS will be covered by Schleswig-Holstein; other activities will be covered by general budget for WSFI activities.
| Wadden Sea Flyway Initiative | Capacity building of WH sites along EAF/training courses/application proposal for IKI project"WSFI capacity building project 2020-2021. Decison on IKI pending Preparation of 2021 Flyway counting." | 168000 | 50000 | 15000 | 103000 | "The capacity building will be funded by BMU with €50,000in 2021. It will contain several sub-projects: - training and courses bird protection, - management of wetlands, - awareness raising and information centres, - support in conferences (PAOC), - activities in framewotk of potetntial WSFI IKI project The flyway monitoring 2021 (after full count in 2020, in 2021 in key sites along the flyway) is fully supported by LNV by a direct assignment to the executive organisation Sovon. The Danish contribution also supports this monitoring programme. Further communication of WSFI by microwebsite is envisaged to be covered by core budget.
|  | Arctic WSFI workshop (POSTPONED TO 2021) | 0 | 30000 | 0 | 0 | Implementation of Flyway Vision in the framework of WSFI. Integration arctic breeding grounds into WSFI. Workshop of WSFI partners with researchers from Arctic countries. Prioritization future support in monitoring, capacity building, research, communication and cooperation. Workshop further postponed from 2019 to 2021. Budget already confirmed and transferred by Germany (SH) in 2019.
WH Brand Management | Brand Activation and Management | Brand activation various target audiences and stakeholders: - Brand activation guidebook (transnational concept and local implementation) 39,500) - Brand visualization and communication material and modules (e.g. flyers, videos social media) for various target audiences (40,500) - Online branding toolbox for co-branding (47,000) | 0 |  | 0 | 0 | No additional funding from state parties required as it is covered by PROWAD LINK according project work plan 2018 - 2021 (see separate table)
Outreach and Communication | WH Education Strategy | Contract with IWSS (WWF): Implementation of the WH Education Strategy, adopted at the Leeuwarden Conference | 40000 | 15000 | 10000 | 15000 | Continuation of networking and communication activities, connecting regional education networks. Development and/or update of trilateral interpretation material, according WH Interpretation Strategy 2018. Work plan 2020-2022 was adopted at WSB 30. Finance proposal was adopted: NL €15.000, Dk €10.000 (Shared between DK-EPA & National Park), Ge €15000. (In Germany the share is divided between SH: € 5000, NLPV NDS €5000 and NP HH €5000).
| Evaluation of TWSC communication strategy | Evaluation of the 2013 TWSC communication strategy with emphasis on interactive online communication opportunities with support of external consultant: possible workshop or interview round with the TWSC member organisations. Including revision of publications layout to match annual report. | 15000 | 6500 | 2000 | 6500 | First phase of review: CWSS internal evaluation of strategy with focus on online communication and identification of major elements in need of update in 4Q/2020; Second phase: with support of external agency evaluation in workshop (alternative: interviews) with TWSC member organisations develop updates for said elements; preparatory work for SIMP chapter on communication + relaunch of Wadden Sea Ecosystem layout to match current TWSC design (e.g. annual report). to be extended in 2022 in case of budget deficit
| WH Social Media | Extension of WH communication on social media channels (Facebook, Twitter, Instagram, Youtube), DNA mapping, sharing and placing contents. Further development of strategy and cooperation with partners (action plan, workshop). | 4000 | 2000 | 0 | 2000 | Annual workshop with support from external experts.
Develop and enhance sustainable tourism (ST) / implementation Action Plan NG-ST | WH awareness raising at yearly ITB (Berlin) - resigned to participating 2021 instead development of a virtual event platform for networking & engagement | Awareness raising platform Word Heritage stand at ITB (showcasing the trilateral cooperation, non-commercial with partners from regional, national or international level as UNESCO). | 12000 | 7000 | 0 | 5000 | Previous years budget costs : € 20,000. Basic costs (floor rental) of € 14,000 to be covered by the Trilateral Cooperation . (D share: SH 3,000 €, NLPV NDS 3,000 €, NP HH 1,000 €).Connection with stakeholder platform stand provided by PROWAD LINK WP2 (B2B and B2C) (see separate table). In 2021 the set-up of a virtual ITB is much more costly compared to a physical event as external expertise and technolgy is needed while the physical event in the past was mainly organized and implemented with in-house expertise. € 14.000 a minimum to have a decent, professional looking appearance, including digital ITB-subscription costs expected to amount to 4000.
Support & promote Regional Sustainable Development in connection with Nature Protection | Partnership development/Partnership Hub | Start-up phase of PH 2020-2022, Engaging further strategic partner and development of joint projects. | 65000 | 35000 | 10000 | 20000 | For the start-up phase of the Partnership Hub a project officer has been attracted on a temporary one-year contract (in connection co-financed by PROWAD Link). For support to project development application (for funding) 65.000 is foreseen (e.g. support to shipping issue in connection to WST proposal, up to 40.000; preparation and facilitation for furthering project proposals by networking activities and workshops moderation 7000, for developing new topics like e.g. Ocean and Health 10.000 ; external support in project develoment phase 8000), as well as 10000 for a basic communication plan development especially under these Covid-19 circumstances. Connection with WP 4 of PROWAD LINK (see separate table). All other activities within CB
| Sustainable Development with focus on Sustainable Transport | Implementation of NG-ST Action Plan: Sustainable Transport (5) . TO BE DEVELOPED UNDER PH (budgetline 16) | 2000 | 0 | 0 | 2000 | A workshop/symposium to exchange experiences and vision on sustainable transport in connection with WSWH with external experts (NG-ST Action Plan 5). No direct link to PROWAD LINK but transport is seen by NG-ST as a major component of sustainable development and is mainstreamed across several SDGs and targets. Activity contributes to the task given to the NG-ST by the board and is seen as preparatory and important step towards fulfilling the Leeuwarden Declaration (LD para. 4)
Wolrd Heritage Foundation | Establisment of a trilateral Wadden Sea World Heritage Foundation | Support for communication and engagement work and advice; advice on several (legal) and administrative (trans)national issues. | 15000 | 5000 | 5000 | 5000 | Specific studies envisaged to support the establishment of this international Foundation according to German law, but granting the same rights and benefits for potential sponsors within the 3 countries. Actual costs for establishing the Foundation including additional project staff for the WHF foreseen in Supplementary Budget 2022 onwards.
Note on F12: BMU - N I 3: Equal share from the Länder
Note on F14: BMU - N I 3: Possibly paid by SH. Won't this become part of the core budget?
Note on F15: BMU - N I 3: Financing via PROWADLINK Budget?? Detailed projectproposal/ description needed
Note on F16: BMU - N I 3: 25.000 + 10.000 (from row 19) and possible some extra money for the WST aplication
Note on F17: BMU - N I 3: BMU - N I 3: Not ready for decision. Needs discussion in OP Team Possibly financed via general budget for PH